## Sheet1
Effort estimation chart |  | Estimated Efforts (Man hour )
Item | Tasks
|  | Round#1 |  |  |  |  | AVG
|  | Member1 Aung | Member2 Rubens | Member3 Han | Member4 Kai | Member5 Kaung
|  | Effort | Effort | Effort | Effort | Effort
Familiarize the existing codes | Familiarize the existing codes | 4 | 4 | 4 | 4 | 4 | 4
|  | Reason : Familiarizing with the existing code helps team members understand the overall architecture, structure, and design patterns of the project. | Reason : Familiarizing with the existing code helps team members understand the overall architecture, structure, and design patterns of the project. | Reason : Familiarizing with the existing code helps team members understand the overall architecture, structure, and design patterns of the project. | Reason : Familiarizing with the existing code helps team members understand the overall architecture, structure, and design patterns of the project. | Reason : Familiarizing with the existing code helps team members understand the overall architecture, structure, and design patterns of the project.
Restructuring of the database | Restructuring of the database | 4 | 4 | 4 | 4 | 4 | 4
|  | Reason : Improve indexing and normalization to enhance query performance and data retrieval speed. | Reason : Refactor relationships between tables to reduce redundancy and improve maintainability. | Reason : Optimize the schema to support new features and ensure backward compatibility. | Reason : Restructure to handle larger datasets efficiently, ensuring scalability under increased load. | Reason : Ensure the database adheres to best practices for data integrity and consistency.
Create github workflow | Create github workflow | 4 | 4 | 4 | 4 | 4 | 4
|  | Reason : Automates basic build and test pipelines to ensure code quality during commits and pull requests. | Reason : Sets up CI/CD for seamless integration with deployment environments with minimal setup required. | Reason : Includes custom steps for running unit tests, linting, and generating build artifacts. | Reason : Requires integration with third-party tools for deployment and advanced notifications in Slack or email. | Reason : Ensures compatibility with multiple branches and handles environment-specific configurations dynamically.
Create components | Create header.js | 2 | 2 | 3 | 3 | 1 | 2
|  | Reason: Basic JavaScript setup for a reusable component. | Reason: Integration with other existing components with minimal debugging required. | Reason: Includes handling session-related data to display user-specific information. | Reason: Requires conditional rendering for notifications and profile dropdown. | Reason: Must ensure compatibility with multiple pages and dynamic data fetching for notifications.
| Create piechart.js Backend | 2 | 2 | 2 | 3 | 2 | 2
|  | Reason: Basic setup for data aggregation logic. | Reason: Fetching and transforming task-related data into a suitable format for charting. | Reason: Ensuring the backend supports dynamic data updates and filters. | Reason: Requires validation of input data and handling of edge cases for missing or incorrect data. | Reason: Includes performance optimization to support large datasets and concurrent user requests.
User log in | Create login.html Frontend | 2 | 3 | 3 | 3 | 2 | 3
|  | Reason: Set up the basic HTML structure, including input fields for email and password. | Reason: Apply basic CSS styling for alignment and spacing to make the form visually presentable. | Reason: Implement client-side validation to ensure required fields are filled and email format is valid. | Reason: Add interactive feedback such as input focus highlights and error messages for invalid inputs. | Reason: Make the form responsive to ensure it works well on different devices, like mobile and tablets.
| Develop login() Backend | 2 | 3 | 3 | 2 | 3 | 3
|  | Reason: Set up a basic API endpoint for handling login requests. | Reason: Validate user credentials by querying the database. | Reason: Implement token generation (e.g., JWT) for user authentication. | Reason: Add error handling for invalid credentials or inactive accounts. | Reason: Implement rate-limiting to prevent brute force attacks.
User log in | Create myproject.html Frontend | 3 | 3 | 2 | 2 | 3 | 3
|  | Reason: Basic HTML structure setup with a header, main section, and footer. | Reason: Integrate responsive layout using CSS for cross-device compatibility. | Reason: Add dynamic placeholders for displaying project details fetched from the backend. | Reason: Create reusable components for project cards and pagination (if applicable). | Reason: Ensure accessibility (ARIA roles, semantic HTML) and basic testing for UI responsiveness.
| Develop getProjectNames() where user is a prodject manager Backend | 2 | 2 | 2 | 2 | 3 | 2
|  | Reason: Implement role validation to ensure the user is a project manager before querying. | Reason: Add filters to fetch projects only assigned to the logged-in project manager. | Reason: Write a basic function to query the database for project names assigned to the project manager. | Reason: Optimize the database query for performance with indexed fields and efficient joins. | Reason: Handle error cases (e.g., no projects found, unauthorized access) and write unit tests.
| Develop CRUD Backend | 2 | 3 | 2 | 2 | 3 | 2
|  | Reason: Develop basic Create operation to insert data into the database with minimal validation. | Reason: Implement Read operations with query filters and pagination for performance. | Reason: Develop Update functionality with field-level validation and concurrency checks. | Reason: Implement Delete operation with soft delete (e.g., status flag) to avoid data loss. | Reason: Integrate logging and auditing for all CRUD operations to track changes and ensure compliance.
| Integerating frontend and backend and debugging (if necessary) | 3 | 3 | 3 | 3 | 2 | 3
|  | Reason: Set up API endpoints and ensure correct connection to frontend using fetch/axios calls. | Reason: Validate data flow between frontend inputs and backend responses, ensuring proper data formatting and error handling. | Reason: Debug mismatches in UI updates (e.g., stale states, incorrect rendering) caused by asynchronous operations. | Reason: Address API-related issues such as CORS, authentication, and status codes for error handling. | Reason: Conduct end-to-end testing to identify and resolve bugs across integrated modules and improve performance.
Assigned project page | Create assignedProjects.html Frontend | 3 | 2 | 2 | 2 | 3 | 2
|  | Reason: Add event listeners to capture user interactions for navigation and project selection. | Reason: Test the layout across multiple devices and browsers for cross-compatibility. | Reason: Integrate dropdowns and search filters to display projects dynamically. | Reason: Build the basic structure of the HTML file with proper semantic tags and placeholders. | Reason: Design the layout using CSS to ensure responsive and user-friendly UI, aligning with existing style guides.
| Develop getTasks() for each assigned projects Backend | 2 | 3 | 2 | 2 | 2 | 2
|  | Reason: Define the query to retrieve tasks for a given project ID, ensuring correct relationships are selected in the schema. | Reason: Optimize the query to handle large datasets using pagination or batch fetching techniques if necessary. | Reason: Implement the function in the backend logic, ensuring correct handling of filters like task status or priority. | Reason: Write and execute unit tests to validate the function's correctness and performance across edge cases. | Reason: Ensure proper error handling and logging for debugging in case of API or database failures.
| Develop CRUD Backend | 2 | 3 | 2 | 2 | 2 | 2
|  | Reason: Define the Create, Read, Update, and Delete functions based on the database schema. | Reason: Implement the database queries for each operation, ensuring relational integrity (e.g., cascading deletes). | Reason: Write robust middleware for validating input data and ensuring secure access control. | Reason: Write and run unit tests to validate CRUD functionality, including edge cases and concurrency handling. | Reason: Optimize CRUD performance for large datasets and ensure proper error handling and logging.
| Integerating frontend and backend and debugging (if necessary) | 2 | 2 | 2 | 2 | 3 | 2
|  | Reason: Align API endpoints with frontend requests and ensure correct data mapping between UI components and backend services. | Reason: Resolve any CORS issues, authentication token mismatches, or endpoint errors during integration testing. | Reason: Debug and fix issues related to state management in the frontend when communicating with backend APIs. | Reason: Conduct thorough end-to-end testing, identify inconsistencies, and address bugs across various workflows. | Reason: Optimize API responses and frontend rendering for better performance and a seamless user experience.
All tasks page | Create alltask.html | 2 | 3 | 2 | 2 | 3 | 2
|  | Reason: Build a basic layout for the "All Tasks" page, including a header, task container, and placeholders for content. | Reason: Integrate a dropdown filter for task statuses, ensuring proper alignment and responsive design. | Reason: Add functionality to dynamically populate tasks using JavaScript and style task cards for a clean UI. | Reason: Ensure tasks can be searched and filtered effectively with real-time updates in the frontend. | Reason: Conduct accessibility and responsiveness tests to ensure the page works seamlessly across all devices.
| Develop CRUD Backend | 3 | 2 | 2 | 2 | 3 | 2
|  | Reason: Set up the database schema and establish relationships between tables/entities for the CRUD operations. | Reason: Implement Create and Read functionalities for each entity, ensuring data validation and error handling. | Reason: Develop Update and Delete endpoints with strict permission checks and consistent validation mechanisms. | Reason: Test all CRUD functionalities using tools like Postman, ensuring API consistency and compliance with requirements. | Reason: Optimize query performance and add logging for debugging and monitoring CRUD operations.
| Add the filtering option for the user to filter the tasks by status frontend | 3 | 3 | 2 | 2 | 3 | 3
|  | Reason: Design and implement a dropdown menu in the UI for filtering tasks by status (e.g., Pending, In Progress, Completed). | Reason: Add JavaScript to capture dropdown changes and dynamically update the displayed task list based on the selected status. | Reason: Ensure the filtered task list integrates smoothly with the existing UI and does not affect other features like pagination or search. | Reason: Test the filter functionality on various devices and browsers to ensure compatibility and responsiveness. | Reason: Optimize the filtering process for larger task lists and ensure the dropdown updates seamlessly without page reloads.
| Integerating frontend and backend and debugging (if necessary) | 3 | 2 | 2 | 3 | 2 | 2
|  | Reason: Connect the frontend task filtering dropdown to the backend endpoint, ensuring status-based filtering works dynamically. | Reason: Debug and resolve any discrepancies between frontend requests and backend responses, such as status codes or incorrect task data. | Reason: Verify data consistency between the UI and database, ensuring tasks are displayed accurately after filtering. | Reason: Perform end-to-end testing to validate that the integrated system works as expected in different environments (e.g., staging, production). | Reason: Optimize data flow between the frontend and backend, reducing latency for large datasets and ensuring smooth performance.
Manage a project | Create manageProject html | 2 | 3 | 2 | 2 | 3 | 2
|  | Reason: Set up the basic structure of the HTML page, including placeholders for project information, task lists, and user roles. | Reason: Design and implement UI components like project cards, task tables, and role assignment sections using CSS for responsiveness. | Reason: Add interactivity to the UI, such as dropdowns, modals, or buttons for managing project details. | Reason: Integrate accessibility and responsive design features to ensure the page works across devices and meets usability standards. | Reason: Collaborate with team members to test and refine the UI layout, ensuring compatibility with backend integration.
| Adjust the existing backend into the project (for project manager and for developer sides)- role based | 3 | 2 | 2 | 3 | 2 | 2
|  | Reason: Analyze the current backend structure and identify the points where role-based differentiation is required. | Reason: Implement role-based middleware or access control logic to restrict or allow specific actions for project managers and developers. | Reason: Update the APIs to handle role-based logic, ensuring endpoints behave differently based on the user's role. | Reason: Conduct extensive testing of role-based behavior in backend functions and APIs to identify inconsistencies or bugs. | Reason: Optimize the role-based logic for performance and ensure proper error handling for unauthorized access scenarios.
| Adjust the existing frontend into the project (for project manager and for developer sides)- role based | 3 | 2 | 3 | 2 | 3 | 2
|  | Reason: Analyze the current UI components and identify where role-based customizations are required (e.g., hiding/showing elements). | Reason: Modify navigation and menu structures to show different options for project managers and developers. | Reason: Update individual pages to conditionally display content based on the user's role (e.g., project list for managers vs. assigned tasks for developers). | Reason: Add role-based logic to ensure seamless transitions between pages and protect restricted views. | Reason: Perform testing to ensure role-specific frontends behave as intended and make adjustments for consistency across devices.
| Integerating frontend and backend and debugging (if necessary) | 3 | 3 | 2 | 3 | 2 | 3
|  | Reason: Set up API endpoints and establish connections between frontend components and backend services. | Reason: Validate data flow between frontend and backend (e.g., forms, CRUD operations) to ensure correct behavior. | Reason: Debug issues with state management or data binding caused during integration. | Reason: Test role-based features to confirm correct data rendering for project managers and developers. | Reason: Conduct end-to-end testing to verify overall system stability and ensure all features work as expected.
Create_new_project popup | Create the frontend popup | 2 | 2 | 3 | 3 | 2 | 2
|  | Reason: Design a simple popup layout and modal structure using HTML and CSS. | Reason: Add JavaScript for opening and closing the popup dynamically. | Reason: Include form fields or action buttons, ensuring responsive behavior. | Reason: Validate inputs (if any) and integrate localStorage for state retention if needed. | Reason: Conduct cross-browser testing and finalize accessibility improvements.
| Integerating frontend and backend and debugging (if necessary) | 3 | 3 | 3 | 2 | 3 | 3
|  | Reason: Connect APIs with frontend functionality to retrieve and display data. | Reason: Test API endpoints and ensure error handling for incorrect responses. | Reason: Debug frontend rendering issues and ensure accurate data binding. | Reason: Optimize API calls to minimize latency and improve user experience. | Reason: Conduct end-to-end testing for all integrated features, fixing edge cases.
Create_new_project popup | Make an interface for the user to display their particulars + log out button to log out | 2 | 3 | 2 | 3 | 3 | 3
|  | Create the HTML structure and layout for user particulars and log out button. | Fetch user particulars from the backend and display them dynamically on the interface. | Implement functionality to clear session/localStorage and redirect to the login page on logout. | Debug issues with user data rendering and logout process, ensuring secure session management. | Conduct comprehensive testing for responsiveness, accessibility, and edge-case handling.
| Allow user to choose avatars | 2 | 2 | 3 | 3 | 2 | 2
|  | Create the frontend UI to display available avatars in a grid or modal. | Fetch available avatar options from the backend dynamically and display them on the interface. | Implement functionality to update the user's profile with the selected avatar, saving to the database. | Debug and ensure selected avatar updates instantly on the frontend and reflects across user sessions. | Test for compatibility across devices and edge cases, such as missing or invalid avatar images, ensuring user-friendly error handling.
| Develop user detail CRUD backend | 3 | 2 | 3 | 3 | 2 | 3
|  | Implement the Create functionality to add new user details to the database. | Develop Read functionality to fetch user details based on filters or unique identifiers. | Implement Update functionality to allow modifications to existing user details. | Develop Delete functionality to safely remove user details while ensuring proper error handling and validations. | Perform testing for CRUD operations, debugging issues, and ensuring proper response handling for edge cases.
| Create front end for user detail CRUD | 2 | 3 | 3 | 2 | 3 | 3
|  | Design the UI components for user detail form (input fields, labels, buttons). | Implement the Create and Read functionality UI for adding and viewing user details. | Develop the Update UI to allow modifications to user details dynamically. | Implement Delete functionality with proper confirmation modal for user actions. | Perform user testing, debug layout issues, and ensure a responsive and accessible interface.
| Integerating frontend and backend and debugging (if necessary) | 3 | 2 | 3 | 3 | 2 | 3
|  | Connect APIs to frontend functionality to send and retrieve data. | Test API responses to ensure data accuracy and handle errors gracefully. | Debug frontend rendering issues to ensure proper data binding and updates. | Optimize API calls to reduce latency and improve responsiveness in the application. | Conduct end-to-end testing, addressing edge cases and resolving discrepancies between UI and backend behavior.
Create new project page | Create createProject.html | 2 | 3 | 3 | 2 | 3 | 3
|  | Design the basic HTML structure for project creation fields. | Add form validation for required fields (e.g., name, description). | Implement a responsive layout to ensure usability on all devices. | Integrate user-friendly features like tooltips or placeholder text for input guidance. | Test the form’s usability and appearance across different browsers, ensuring consistency.
| Integerating frontend and backend and debugging (if necessary) | 2 | 2 | 2 | 3 | 2 | 2
|  | Connect APIs with the frontend to enable data retrieval and submission. | Verify and handle API response errors for smoother user experience. | Debug and resolve data-binding or rendering issues on the frontend. | Optimize API integration for performance, reducing latency and improving UX. | Conduct end-to-end testing for all features, addressing edge cases and bugs.
Update project page | Create updateproject.html | 3 | 2 | 3 | 3 | 2 | 3
|  | Design and structure the basic layout of the update project page. | Add interactive form elements for editing project details. | Ensure proper validation for form inputs (e.g., required fields). | Style the page for consistency with the existing UI, ensuring responsiveness. | Test UI functionality thoroughly and fix any layout or interaction issues.
| Integerating frontend and backend | 2 | 2 | 3 | 3 | 2 | 2
|  | Connect APIs with frontend elements to retrieve project data. | Validate form submissions and ensure accurate data flow to the backend. | Handle edge cases like invalid inputs or missing data during integration. | Debug and resolve communication issues between frontend and backend. | Perform end-to-end testing to ensure seamless functionality and fix any issues.
Notifications for application workflows | Create backend for notifications | 4 | 2 | 3 | 3 | 2 | 3
|  | Define a database schema/model for notifications and notification recipients. | Set up the basic structure for handling notifications in the backend. | Implement APIs for creating, retrieving, and marking notifications as read/unread. | Add validation for API inputs (e.g., required fields, valid recipient IDs). | Test API endpoints thoroughly, ensuring functionality and data integrity.
| Create front end for notifications | 2 | 3 | 3 | 2 | 3 | 3
|  | Design and structure the basic layout for the notifications interface. | Implement functionality to fetch and display notifications dynamically via API. | Add interactive elements to display notifications (e.g., a dropdown or sidebar). | Style the notifications UI to ensure consistency with the existing design and responsiveness. | Test the notifications UI thoroughly for proper interaction and seamless user experience.
| Create prisma model for notification tables | 3 | 3 | 2 | 3 | 3 | 3
|  | Define the Notification model to include fields like id, title, message, type, createdAt, and updatedAt. | Define the NotificationRecipient model to associate notifications with recipients, including fields like id, notificationId, recipientId, and status (e.g., read/unread). | Establish relationships between the Notification and NotificationRecipient models, ensuring proper foreign key constraints. | Add validation rules and default values for fields like createdAt, status, and updatedAt. | Test the Prisma schema by running migrations and verifying the database structure.
| Integerating frontend and backend and debugging (if necessary) | 4 | 3 | 4 | 3 | 4 | 4
|  | Reason: Set up API endpoints and establish connections between frontend components and backend services. | Reason: Validate data flow between frontend and backend (e.g., forms, CRUD operations) to ensure correct behavior. | Reason: Debug issues with state management or data binding caused during integration. | Reason: Test role-based features to confirm correct data rendering for project managers and developers. | Reason: Conduct end-to-end testing to verify overall system stability and ensure all features work as expected.
| Total | 100 | 100 | 100 | 100 | 100

## ProdBacklog
Prioritization | Product Backlog Item | Effort Estimation (manhour)
1 | Familiarize the existing codes | 2
1 | Restructuring of the database | 3
1 | Create github workflow | 5
1 | Create components | 5
| Create header.js | 3
| Create piechart.js Backend | 2
1 | User log in | 5
| Create login.html Frontend | 2
| Develop login() Backend | 3
1 | My project page | 13
| Create myproject.html Frontend | 3
| Develop getProjectNames() where user is a prodject manager Backend | 3
| Develop CRUD Backend | 4
| Integerating frontend and backend and debugging (if necessary) | 3
1 | Assigned project page | 14
| Create assignedProjects.html Frontend | 3
| Develop getTasks() for each assigned projects Backend | 4
| Develop CRUD Backend | 4
| Integerating frontend and backend and debugging (if necessary) | 3
1 | All tasks page | 10
| Create alltask.html | 3
| Develop CRUD Backend | 3
| Add the filtering option for the user to filter the tasks by status frontend | 1
| Integerating frontend and backend and debugging (if necessary) | 3
1 | Manage a project | 12
| Create manageProject html | 3
| Adjust the existing backend into the project (for project manager and for developer sides)- role based | 3
| Adjust the existing frontend into the project (for project manager and for developer sides)- role based | 3
| Integerating frontend and backend and debugging (if necessary) | 3
1 | Create_new_project popup | 6
| Create the frontend popup | 3
| Integerating frontend and backend and debugging (if necessary) | 3
2 | User profile session | 13
| Make an interface for the user to display their particulars + log out button to log out | 2
| Allow user to choose avatars | 2
| Develop user detail CRUD backend | 3
| Create front end for user detail CRUD | 3
| Integerating frontend and backend and debugging (if necessary) | 3
1 | Create new project page | 6
| Create createProject.html | 3
| Integerating frontend and backend and debugging (if necessary) | 3
1 | Update project page | 6
| Create updateproject.html | 3
| Integerating frontend and backend | 3
2 | Notifications for application workflows | 10
| Create backend for notifications | 3
| Create front end for notifications | 3
| Create prisma model for notification tables | 1
| Integerating frontend and backend and debugging (if necessary) | 3