## Sheet1
Prioritization | Product Backlog Item | Effort Estimation (manhour)
1 | Familiarize the existing codes | 2
1 | Restructuring of the database | 3
1 | Create github workflow | 5
1 | Create components | 5
| Create header.js | 3
| Create piechart.js Backend | 2
1 | User log in | 5
| Create login.html Frontend | 2
| Develop login() Backend | 3
1 | My project page | 13
| Create myproject.html Frontend | 3
| Develop getProjectNames() where user is a prodject manager Backend | 3
| Develop CRUD Backend | 4
| Integerating frontend and backend and debugging (if necessary) | 3
1 | Assigned project page | 14
| Create assignedProjects.html Frontend | 3
| Develop getTasks() for each assigned projects Backend | 4
| Develop CRUD Backend | 4
| Integerating frontend and backend and debugging (if necessary) | 3
1 | All tasks page | 10
| Create alltask.html | 3
| Develop CRUD Backend | 3
| Add the filtering option for the user to filter the tasks by status frontend | 1
| Integerating frontend and backend and debugging (if necessary) | 3
1 | Manage a project | 12
| Create manageProject html | 3
| Adjust the existing backend into the project (for project manager and for developer sides)- role based | 3
| Adjust the existing frontend into the project (for project manager and for developer sides)- role based | 3
| Integerating frontend and backend and debugging (if necessary) | 3
1 | Create_new_project popup | 6
| Create the frontend popup | 3
| Integerating frontend and backend and debugging (if necessary) | 3
2 | User profile session | 13
| Make an interface for the user to display their particulars + log out button to log out | 2
| Allow user to choose avatars | 2
| Develop user detail CRUD backend | 3
| Create front end for user detail CRUD | 3
| Integerating frontend and backend and debugging (if necessary) | 3
1 | Create new project page | 6
| Create createProject.html | 3
| Integerating frontend and backend and debugging (if necessary) | 3
1 | Update project page | 6
| Create updateproject.html | 3
| Integerating frontend and backend | 3
2 | Notifications for application workflows | 10
| Create backend for notifications | 3
| Create front end for notifications | 3
| Create prisma model for notification tables | 1
| Integerating frontend and backend and debugging (if necessary) | 3