## End of Sprint1
SCRUM BOARD (at the end of Sprint 1)
2024-11-12
BACKLOG | NOT STARTED | IN PROGRESS | DONE
Familiarize the existing codes
Restructuring of the database
Create Github workflow
Create components
User log in
My project page
Assigned project page
All tasks page
Manage a project
Create_new_project popup
Update project popup
User profile session
3hr
Create piechart.js backend
KAI, RUBENS
2hr
Create header.js
KAUNG
3hr
Develop login() backend
KAI
2hr
Create user log in html frontend
HAN
4hr
Develop MYprojects CRUD backend RUBENS
4hr
Create myproject.html frontend
KAUNG, HAN
4hr
Develop getProjectNames() where user is a prodject manager Backend
3hr
Integerating frontend and backend and debugging (if necessary)
4hr
Create assignedProjects.html Frontend
4hr
Develop getTasks() for each assigned projects Backend
5hr
Recognize the folder structures and existing codes of the project
KAUNG, AUNG, HAN, KAI, RUBENS
2hr
Recognize the folder structures and existing codes of the project
KAUNG, AUNG, HAN, KAI, RUBENS
3hr
Restructure the entire database table structure, populate new and/or update prisma models
KAUNG, AUNG, HAN, KAI, RUBENS
4hr
Develop Assigned Projects CRUD Backend
3hr
Integerating frontend and backend and debugging (if necessary)
4hr
Create alltask.html
4hr
Develop task CRUD Backend
2hr
Add the filtering option for the user to filter the tasks by status frontend
3hr
Integerating frontend and backend and debugging (if necessary)
3hr
Create manageProject html
3hr
Adjust the existing backend into the project (for project manager and for developer sides)- role based
3hr
Integerating frontend and backend and debugging (if necessary)
3hr
Create the frontend popup
3hr
Integerating frontend and backend and debugging (if necessary)
2hr
Make an interface for the user to display their particulars + log out button to log out
2hr
Allow user to choose avatars
3hr
Develop user detail CRUD backend
3hr
Integerating frontend and backend and debugging (if necessary)
3hr
Create updateproject popup frontend
3hr
Integerating frontend and backend and debugging (if necessary)
3hr
Create frontend for user detail CRUD
5hr
Restructure the entire database table structure, populate new and/or update prisma models
AUNG

## End of Sprint2
SCRUM BOARD (at the end of Sprint 2)
2024-11-19
BACKLOG | NOT STARTED | IN PROGRESS | DONE
Familiarize the existing codes
Restructuring of the database
Create Github workflow
Create components
User log in
My project page
Assigned project page
All tasks page
Manage a project
Create_new_project popup
Update project popup
User profile session
3hr
Create piechart.js backend
AUNG, KAI, RUBENS
2hr
Create header.js
KAUNG
3hr
Develop login() backend
KAI
2hr
Create user log in html frontend
HAN
4hr
Develop MYprojects CRUD backend RUBENS
4hr
Create myproject.html frontend
KAUNG, HAN
4hr
Develop getProjectNames() where user is a prodject manager Backend
KAI
3hr
Integerating frontend and backend and debugging (if necessary)
HAN, KAI
4hr
Create assignedProjects.html Frontend
KAUNG
4hr
Develop getTasks() for each assigned projects Backend
AUNG
5hr
Recognize the folder structures and existing codes of the project
KAUNG, AUNG, HAN, KAI, RUBENS
5hr
Recognize the folder structures and existing codes of the project
KAUNG, AUNG, HAN, KAI, RUBENS
5hr
Restructure the entire database table structure, populate new and/or update prisma models
KAUNG, AUNG, HAN, KAI, RUBENS
4hr
Develop Assigned Projects CRUD Backend
3hr
Integerating frontend and backend and debugging (if necessary)
4hr
Create alltask.html
HAN
4hr
Develop task CRUD Backend
RUBENS
2hr
Add the filtering option for the user to filter the tasks by status frontend
HAN, KAUNG
3hr
Integerating frontend and backend and debugging (if necessary)
HAN, RUBENS
3hr
Create manageProject html
3hr
Adjust the existing backend into the project (for project manager and for developer sides)- role based
3hr
Integerating frontend and backend and debugging (if necessary)
3hr
Integerating frontend and backend and debugging (if necessary)
2hr
Make an interface for the user to display their particulars + log out button to log out
2hr
Allow user to choose avatars
3hr
Develop user detail CRUD backend
3hr
Integerating frontend and backend and debugging (if necessary)
3hr
Create updateproject popup frontend
3hr
Integerating frontend and backend and debugging (if necessary)
3hr
Create frontend for user detail CRUD
3hr
Create the frontend popup
3hr
Create piechart.js backend
KAI, RUBENS
2hr
Create header.js
KAUNG
3hr
Develop login() backend
KAI
2hr
Create user log in html frontend
HAN
5hr
Recognize the folder structures and existing codes of the project
KAUNG, AUNG, HAN, KAI, RUBENS
2hr
Recognize the folder structures and existing codes of the project
KAUNG, AUNG, HAN, KAI, RUBENS
3hr
Restructure the entire database table structure, populate new and/or update prisma models
KAUNG, AUNG, HAN, KAI, RUBENS
5hr
Restructure the entire database table structure, populate new and/or update prisma models
AUNG

## End of Sprint3
SCRUM BOARD (at the end of Sprint 3)
2024-11-26
BACKLOG | NOT STARTED | IN PROGRESS | DONE
Familiarize the existing codes
Restructuring of the database
Create Github workflow
Create components
User log in
My project page
Assigned project page
All tasks page
Manage a project
Create_new_project popup
Update project popup
User profile session
User notification
3hr
Create piechart.js backend
AUNG, KAI, RUBENS
2hr
Create header.js
KAUNG
3hr
Develop login() backend
KAI
2hr
Create user log in html frontend
HAN
4hr
Develop MYprojects CRUD backend RUBENS
4hr
Create myproject.html frontend
KAUNG, HAN
4hr
Develop getProjectNames() where user is a prodject manager Backend
KAI
3hr
Integerating frontend and backend and debugging (if necessary)
HAN, KAI
4hr
Create assignedProjects.html Frontend
KAUNG
4hr
Develop getTasks() for each assigned projects Backend
AUNG
5hr
Recognize the folder structures and existing codes of the project
KAUNG, AUNG, HAN, KAI, RUBENS
5hr
Recognize the folder structures and existing codes of the project
KAUNG, AUNG, HAN, KAI, RUBENS
5hr
Restructure the entire database table structure, populate new and/or update prisma models
KAUNG, AUNG, HAN, KAI, RUBENS
4hr
Develop Assigned Projects CRUD Backend
AUNG
3hr
Integerating frontend and backend and debugging (if necessary)
4hr
Create alltask.html
HAN
4hr
Develop task CRUD Backend
RUBENS
2hr
Add the filtering option for the user to filter the tasks by status frontend
HAN, KAUNG
3hr
Integerating frontend and backend and debugging (if necessary)
HAN, RUBENS
3hr
Create manageProject html
KAUNG
3hr
Adjust the existing backend into the project (for project manager and for developer sides)- role based
AUNG
3hr
Integerating frontend and backend and debugging (if necessary)
KAUNG, AUNG
3hr
Integerating frontend and backend and debugging (if necessary)
RUBENS
2hr
Make an interface for the user to display their particulars + log out button to log out
HAN
2hr
Allow user to choose avatars
HAN
3hr
Develop user detail CRUD backend
KAI
3hr
Integerating frontend and backend and debugging (if necessary)
3hr
Create updateproject popup frontend
KAUNG
3hr
Integerating frontend and backend and debugging (if necessary)
3hr
Create frontend for user detail CRUD
3hr
Create the frontend popup
HAN
3hr
Create piechart.js backend
AUNG, KAI, RUBENS
2hr
Create header.js
KAUNG
3hr
Develop login() backend
KAI
2hr
Create user log in html frontend
HAN
5hr
Recognize the folder structures and existing codes of the project
KAUNG, AUNG, HAN, KAI, RUBENS
5hr
Recognize the folder structures and existing codes of the project
KAUNG, AUNG, HAN, KAI, RUBENS
5hr
Restructure the entire database table structure, populate new and/or update prisma models
KAUNG, AUNG, HAN, KAI, RUBENS
3hr
Create piechart.js backend
KAI, RUBENS
2hr
Create header.js
KAUNG
3hr
Develop login() backend
KAI
2hr
Create user log in html frontend
HAN
5hr
Recognize the folder structures and existing codes of the project
KAUNG, AUNG, HAN, KAI, RUBENS
2hr
Recognize the folder structures and existing codes of the project
KAUNG, AUNG, HAN, KAI, RUBENS
3hr
Restructure the entire database table structure, populate new and/or update prisma models
KAUNG, AUNG, HAN, KAI, RUBENS
5hr
Restructure the entire database table structure, populate new and/or update prisma models
AUNG
3hr
Create backend for Notifications
1hr
Create prisma model for notification tables
3hr
Integerating frontend and backend and debugging (if necessary)
3hr
Create frontend for Notifications

## End of Sprint4
SCRUM BOARD (at the end of Sprint 4)
2024-12-03
BACKLOG | NOT STARTED | IN PROGRESS | DONE
Familiarize the existing codes
Restructuring of the database
Create Github workflow
Create components
User log in
My project page
Assigned project page
All tasks page
Manage a project
Create_new_project popup
Update project popup
User profile session
User notification
3hr
Create piechart.js backend
AUNG, KAI, RUBENS
2hr
Create header.js
KAUNG
3hr
Develop login() backend
KAI
2hr
Create user log in html frontend
HAN
4hr
Develop MYprojects CRUD backend RUBENS
4hr
Create myproject.html frontend
KAUNG, HAN
4hr
Develop getProjectNames() where user is a prodject manager Backend
KAI
3hr
Integerating frontend and backend and debugging (if necessary)
HAN, KAI
4hr
Create assignedProjects.html Frontend
KAUNG
4hr
Develop getTasks() for each assigned projects Backend
AUNG
5hr
Recognize the folder structures and existing codes of the project
KAUNG, AUNG, HAN, KAI, RUBENS
5hr
Recognize the folder structures and existing codes of the project
KAUNG, AUNG, HAN, KAI, RUBENS
5hr
Restructure the entire database table structure, populate new and/or update prisma models
KAUNG, AUNG, HAN, KAI, RUBENS
4hr
Develop Assigned Projects CRUD Backend
AUNG
3hr
Integerating frontend and backend and debugging (if necessary)
KAUNG, AUNG
4hr
Create alltask.html
HAN
4hr
Develop task CRUD Backend
RUBENS
2hr
Add the filtering option for the user to filter the tasks by status frontend
HAN, KAUNG
3hr
Integerating frontend and backend and debugging (if necessary)
HAN, RUBENS
3hr
Create manageProject html
KAUNG
3hr
Adjust the existing backend into the project (for project manager and for developer sides)- role based
AUNG
3hr
Integerating frontend and backend and debugging (if necessary)
KAUNG, AUNG
3hr
Integerating frontend and backend and debugging (if necessary)
RUBENS
2hr
Make an interface for the user to display their particulars + log out button to log out
HAN
2hr
Allow user to choose avatars
HAN
3hr
Develop user detail CRUD backend
KAI
3hr
Integerating frontend and backend and debugging (if necessary)
HAN, KAI
3hr
Create updateproject popup frontend
KAUNG
3hr
Integerating frontend and backend and debugging (if necessary)
KAUNG, RUBENS
3hr
Create frontend for user detail CRUD
HAN
3hr
Create the frontend popup
HAN
3hr
Create piechart.js backend
AUNG, KAI, RUBENS
2hr
Create header.js
KAUNG
3hr
Develop login() backend
KAI
2hr
Create user log in html frontend
HAN
5hr
Recognize the folder structures and existing codes of the project
KAUNG, AUNG, HAN, KAI, RUBENS
5hr
Recognize the folder structures and existing codes of the project
KAUNG, AUNG, HAN, KAI, RUBENS
5hr
Restructure the entire database table structure, populate new and/or update prisma models
KAUNG, AUNG, HAN, KAI, RUBENS
3hr
Create piechart.js backend
KAI, RUBENS
2hr
Create header.js
KAUNG
3hr
Develop login() backend
KAI
2hr
Create user log in html frontend
HAN
5hr
Recognize the folder structures and existing codes of the project
KAUNG, AUNG, HAN, KAI, RUBENS
2hr
Recognize the folder structures and existing codes of the project
KAUNG, AUNG, HAN, KAI, RUBENS
3hr
Restructure the entire database table structure, populate new and/or update prisma models
KAUNG, AUNG, HAN, KAI, RUBENS
5hr
Restructure the entire database table structure, populate new and/or update prisma models
AUNG
3hr
Create backend for Notifications
KAI, RUBENS
3hr
Create frontend for Notifications
HAN, KAUNG
3hr
Integerating frontend and backend and debugging (if necessary)
KAI, RUBENS, HAN
1hr
Create prisma model for notification tables
AUNG